## Overview
CMAS — Product Roadmap
Course Monitoring & Assessment System for Course Learning Outcomes · Senior Leadership (PM / PO / BA / TPM) · Baseline 2026-07-13
PROJECT SNAPSHOT
Product | CMAS — web platform for instructors to define CLOs, map assessments, enter/import scores, and monitor CLO attainment per course
Type | Undergraduate thesis project (ปริญญานิพนธ์) — full-stack monorepo
Stack | React 19 + React Router 7 (client) · Node + Fastify + TypeScript (server) · Prisma + PostgreSQL/Supabase
Team | 3 developers (Dev A / Dev B / Dev C), module-owned end-to-end
Scope | 15 features · 15 pages · 11 data models — 3 features DONE, 12 remaining
Horizon | 2026-07-13 → 2026-12 (final defense)
STRATEGIC GOALS
G1 | Ship a working CLO-attainment MVP that an instructor can run end-to-end for one real course
G2 | Pass each academic gate (Progress Reports 1–4) on time — timeliness is graded
G3 | Prove CLO attainment analytics with real score data (manual + Excel import)
G4 | Deliver thesis draft (ch.1–3) and defend (CLO 5) with a demoable system
NOW (Jul–Aug) | Phase 3 — Core CLO system build: Curriculum, Course, CLO, Activity, Assessment Criteria mapping
NEXT (Sep–Oct) | Phase 4 — Scoring & analytics: Student roster, Score entry, Excel import/export, Attainment dashboard
LATER (Nov–Dec) | Phase 5 — Integration hardening, UAT on a real course, thesis draft ch.1–3, final defense
HOW TO READ THIS WORKBOOK
Milestones | Phase gates tied to academic Progress Reports + grading weight
Backlog | All 15 features with MoSCoW priority, value/effort, owner, target phase
Timeline | Weekly Gantt (Jul→Dec) across the three developer workstreams
Team & RACI | Ownership split + stakeholder map (advisor, coordinator, committee)
Risks | Top delivery risks with mitigation and owner

## Milestones
Milestones & Academic Gates
Phase gates aligned to CLO Progress Reports · grading weights from the course assessment plan
# | Phase / Gate | CLO | Target date | Key deliverables (exit criteria) | Assessment (weight) | Owner | Status
M0 | Foundation baseline | — | 2026-07-13 | Monorepo, Prisma schema (11 models), design system, dev standards, Auth + User Mgmt + Course List shipped | — (pre-baseline) | All | Done
M1 | Progress Report 1 — Problem & RCA | CLO 1 | 2026-07-27 | Root Cause Analysis, work plan, problem statement approved by advisor | Report 10 + Timeliness 2.5 | PM/BA | Done
M2 | Progress Report 2 — Baseline & criteria | CLO 2 | 2026-08-17 | Assumptions, evaluation criteria, chart-of-accounts of thesis, underlying principles/theory | Report 10 + Timeliness 2.5 | BA/PO | In progress
M3 | Progress Report 3 — Architecture ready | CLO 3 | 2026-09-14 | Project architecture ready for development: data model, page map (15 routes), design system, API contract | Report 10 + Timeliness 2.5 | TPM | In progress
M4 | Progress Report 4 — MVP developed | CLO 4 | 2026-11-09 | 12 remaining features built per architecture: Curriculum→Course→CLO→Activity→Criteria→Score→Dashboard | Report 10 + Timeliness 2.5 | TPM/Devs | Not started
M5 | Final Defense — Summary & present | CLO 5 | 2026-12-14 | Integrated system + UAT on a real course, thesis draft ch.1–3, presentation to committee | Draft 15 + Present 10 + Results 20 | All | Not started

## Backlog
Feature Backlog — Prioritized
15 features from features-pages.md · MoSCoW priority · Value(1-5) / Effort(dev-days) · owner by module · target phase
# | Feature | Model(s) | Priority | Value | Effort (d) | Owner | Phase | Depends on | Status
1 | Authentication (login/JWT session) | User | Must | 5 | 0 | — | P0 | — | Done
2 | User Management (CRUD, roles, active) | User | Must | 4 | 0 | — | P0 | F1 | Done
5 | Course Management — list | Course | Must | 5 | 0 | Dev A | P0 | F2 | Done
3 | Curriculum Management (CRUD, clone) | Curriculum | Must | 4 | 4 | Dev A | P3 | F2 | Not started
4 | Curriculum Course + Template CLO | CurriculumCourse, TemplateCLO | Must | 4 | 5 | Dev A | P3 | F3 | Not started
5b | Course create / overview pages | Course | Must | 5 | 3 | Dev A | P3 | F5 | Not started
6 | CLO Management (CRUD, reorder, threshold) | CLO | Must | 5 | 5 | Dev B | P3 | F5b | Not started
7 | Behavioral Objectives (CRUD per CLO) | BehavioralObjective | Should | 3 | 3 | Dev B | P3 | F6 | Not started
8 | Activity Management (CRUD, weight/maxScore) | Activity | Must | 5 | 5 | Dev B | P3 | F5b | Not started
9 | Assessment Criteria Mapping (Activity↔CLO) | AssessmentCriteria | Must | 5 | 4 | Dev B | P3 | F6, F8 | Not started
10 | Student Roster (CRUD) | Student | Must | 4 | 3 | Dev C | P4 | F5b | Not started
11 | Score Entry (manual per activity) | Score | Must | 5 | 4 | Dev C | P4 | F8, F10 | Not started
12 | Score Import/Export (Excel) | Score, ScoreUploadLog | Must | 5 | 6 | Dev C | P4 | F11 | Not started
13 | Score Upload Log | ScoreUploadLog | Could | 2 | 2 | Dev C | P4 | F12 | Not started
14 | CLO Attainment Dashboard (at-risk) | Score + AssessmentCriteria | Must | 5 | 6 | Dev C | P4 | F9, F11 | Not started
15 | Student Individual Report | Score / Student | Should | 3 | 4 | Dev C | P4 | F14 | Not started
12 features remaining · ~54 dev-days total · split ~ Dev A 15d / Dev B 17d / Dev C 25d — rebalance F15/F13 if Dev C overloads

## Timeline
Delivery Timeline — Weekly Gantt
Baseline 2026-07-13 → mid-Dec 2026 · bars = active work · ◆ = milestone gate · green = done
Workstream | Owner | Phase | Jul |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec
week of → |  |  | 13 | 20 | 27 | 03 | 10 | 17 | 24 | 31 | 07 | 14 | 21 | 28 | 05 | 12 | 19 | 26 | 02 | 09 | 16 | 23 | 30 | 07 | 14
Discovery / RCA + baseline (CLO1–2 docs) | PM/BA | P1–2
Architecture: schema, page map, design sys | TPM | P3 | bar: Jul 13 to Sep 07
A · Curriculum + Course pages | Dev A | P3
B · CLO + Objectives | Dev B | P3 | bar: Jul 27 to Aug 31
B · Activity + Criteria mapping | Dev B | P3
C · Student roster | Dev C | P4 | bar: Sep 07 to Sep 21
C · Score entry + Excel import/export | Dev C | P4
C · Attainment dashboard + student report | Dev C | P4 | bar: Oct 05 to Nov 09
Integration + UAT on a real course | All | P5
Thesis draft ch.1–3 + defense prep | All | P5 | bar: Nov 09 to Dec 14
◆ Milestone gate |  |  | Jul 27: M1; Aug 17: M2; Sep 14: M3; Nov 09: M4; Dec 14: M5
Legend: ■ green = completed ■ blue = planned work ◆ red = milestone / progress-report gate

## Team & RACI
Team, Ownership & Stakeholders
Module ownership (end-to-end: route+component+service+controller) · RACI · stakeholder map
OWNERSHIP (module split)
Person | Module | Features | Pages | Est. days | Notes
Dev A | Curriculum + Course | 3, 4, 5 | /curricula, /courses/new, /courses/:id | 15 | Unblocks CLO & Activity modules — must land first
Dev B | CLO + Activity + Criteria (core) | 6, 7, 8, 9 | /courses/:id/clos, /activities | 17 | Heart of the system; critical path to dashboard
Dev C | Student + Score + Dashboard | 10–15 | /students, /scores, /dashboard | 25 | Heaviest load — consider de-scoping F13/F15 to Could/Should
RACI (key activities)
Activity | Dev A | Dev B | Dev C | Advisor | Coordinator
Requirements & scope sign-off | C | C | C | A | I
Architecture / schema decisions | R | R | R | A | I
Feature implementation | R | R | R | I | -
Progress report submission | R | R | R | A | A
Code review / merge to main | R | R | R | C | -
UAT on a real course | C | C | R | A | C
Final defense | R | R | R | A | I
R = Responsible · A = Accountable · C = Consulted · I = Informed
STAKEHOLDERS
Stakeholder | Role | Interest | Cadence | Channel | Owner
อ.ที่ปรึกษา (Advisor) | Approves reports, grades CLO 1–5 | High / High | Bi-weekly | Meeting + report | PM
อ.ผู้ประสานงานรายวิชา (Coordinator) | Grades timeliness, schedule gate | High / Med | Per gate | Report submission | PM
กรรมการสอบ (Committee) | Final defense evaluation | High / High | Once (Dec) | Defense | All
Instructor end-users | Real users of the CLO system | Med / High | During UAT | UAT sessions | Dev C
Dev team (3) | Build the system | High / High | Daily standup | Chat + repo | TPM

## Risks
Delivery Risks & Mitigation
Top risks to hitting the academic gates and MVP · Impact × Likelihood · owner + mitigation
# | Risk | Impact | Likelihood | Exposure | Mitigation | Owner
R1 | Dev C overloaded (6 features / 25d) delays dashboard — the graded centerpiece | High | High | High | De-scope F13 (log) & F15 (student report) to Should/Could; pair Dev B on dashboard once Criteria mapping lands | TPM
R2 | Score Excel import (F12) more complex than sized (parsing, validation, error rows) | High | Med | High | Spike parsing early (W9); reuse a proven Excel lib; define file template up front; log fail rows via ScoreUploadLog | Dev C
R3 | Critical-path chain (Course→CLO→Activity→Criteria→Score) means slippage compounds | High | Med | High | Front-load Dev A/B in P3; enforce weekly gate demo; keep API contract frozen after M3 | TPM
R4 | Missing a Progress Report date costs timeliness marks (graded) | Med | Med | Med | Calendar all gates now; freeze report content 3 days before each; PM owns submission | PM
R5 | Scope creep beyond the 15 documented features | Med | Med | Med | features-pages.md is the single source of truth; changes go through PO + weekly report | PO
R6 | No real course data for UAT / dashboard validation | Med | Low | Med | Secure one instructor + one course dataset by M3; seed script as fallback | PM
R7 | Deploy friction across Vercel + Railway + Supabase near defense | Low | Med | Med | Stand up all three environments in P3, not P5; smoke-test deploy each sprint | Dev A